## 统计表
统计口径 | item分数优先取 Result；Result 为空时取 Score；多人负责时按负责人数量平分。
Beta1 版本总分 | 1260
wugren: (707.5, 56.15%)
item | item分数 | 属于这个人的分数 | URL
ACMA Automatic Certificate Management | 30 | 30 | https://github.com/buckyos/cyfs-gateway/issues/46
ACME Automatic Certificate Management Support DNS Challenge and HTTP Challenge | 30 | 30 | https://github.com/buckyos/cyfs-gateway/issues/48
Active Connection Management | 15 | 15 | https://github.com/buckyos/cyfs-gateway/issues/30
Beta1 doc | 30 | 30 | https://github.com/buckyos/cyfs-gateway/issues/47
Command Line Implementation | 30 | 30 | https://github.com/buckyos/cyfs-gateway/issues/33
CYFS-Gateway Execution Framework | 30 | 30 | https://github.com/buckyos/cyfs-gateway/issues/28
DNS Inner Service Refactoring | 15 | 15 | https://github.com/buckyos/cyfs-gateway/issues/34
HTTP Server | 40 | 20 | https://github.com/buckyos/cyfs-gateway/issues/37
Packet Interception | 30 | 30 | https://github.com/buckyos/cyfs-gateway/issues/24
Product Logging Library | 15 | 15 | https://github.com/buckyos/cyfs-gateway/issues/29
QUIC Stack | 30 | 30 | https://github.com/buckyos/cyfs-gateway/issues/22
QUIC Tunnel Support | 10 | 10 | https://github.com/buckyos/cyfs-gateway/issues/31
Rate Limiting Implementation | 30 | 30 | https://github.com/buckyos/cyfs-gateway/issues/25
RTCP Refactoring | 10 | 10 | https://github.com/buckyos/cyfs-gateway/issues/26
rtcp stack | 20 | 20 | https://github.com/buckyos/cyfs-gateway/issues/21
SN Inner Service Refactoring | 45 | 45 | https://github.com/buckyos/cyfs-gateway/issues/35
SN refactor | 30 | 30 | https://github.com/buckyos/cyfs-gateway/issues/68
SOCKS5 Server | 25 | 12.5 | https://github.com/buckyos/cyfs-gateway/issues/36
Support for configuring global collections | 20 | 20 | https://github.com/buckyos/cyfs-gateway/issues/65
Support traffic statistics and speed limiting by user | 60 | 60 | https://github.com/buckyos/cyfs-gateway/issues/50
Supports HTTPS request certificate replacement | 30 | 30 | https://github.com/buckyos/cyfs-gateway/issues/49
System Integration | 30 | 30 | https://github.com/buckyos/cyfs-gateway/issues/44
tcp stack | 20 | 20 | https://github.com/buckyos/cyfs-gateway/issues/19
TLS Stack | 20 | 20 | https://github.com/buckyos/cyfs-gateway/issues/23
Tun Device Packet Interception | 45 | 45 | https://github.com/buckyos/cyfs-gateway/issues/32
TunnelManager Refactoring | 10 | 10 | https://github.com/buckyos/cyfs-gateway/issues/27
udp stack | 20 | 20 | https://github.com/buckyos/cyfs-gateway/issues/20
web3 gateway test | 20 | 20 | https://github.com/buckyos/cyfs-gateway/issues/56
lurenpluto: (432.5, 34.33%)
item | item分数 | 属于这个人的分数 | URL
Base Command Implementation | 120 | 120 | https://github.com/buckyos/cyfs-gateway/issues/38
Collection Command Implementation | 60 | 60 | https://github.com/buckyos/cyfs-gateway/issues/40
Process_Chains Framework Implementation | 90 | 90 | https://github.com/buckyos/cyfs-gateway/issues/41
Protocol Detection Command Implementation | 30 | 30 | https://github.com/buckyos/cyfs-gateway/issues/39
SOCKS5 Server | 25 | 12.5 | https://github.com/buckyos/cyfs-gateway/issues/36
Support JS Engine | 90 | 90 | https://github.com/buckyos/cyfs-gateway/issues/45
Support Lib Calling | 30 | 30 | https://github.com/buckyos/cyfs-gateway/issues/43
waterflier: (120, 9.52%)
item | item分数 | 属于这个人的分数 | URL
Constructing a multi-node virtual machine development and testing environment based on multipass | 30 | 30 | https://github.com/buckyos/cyfs-gateway/issues/55
HTTP Server | 40 | 20 | https://github.com/buckyos/cyfs-gateway/issues/37
Impl QA-Server | 30 | 30 | https://github.com/buckyos/cyfs-gateway/issues/51
Implementing Web3 gateway with user-held TLS certificates based on TLS stack. | 30 | 30 | https://github.com/buckyos/cyfs-gateway/issues/53
Process chain日志级别调整 | 10 | 10 | https://github.com/buckyos/cyfs-gateway/issues/62
Beta2 版本总分 | 30
lurenpluto: (15, 50.00%)
item | item分数 | 属于这个人的分数 | URL
cyfs-gateway provides better debugging tools for process chains. | 30 | 15 | https://github.com/buckyos/cyfs-gateway/issues/64
wugren: (15, 50.00%)
item | item分数 | 属于这个人的分数 | URL
cyfs-gateway provides better debugging tools for process chains. | 30 | 15 | https://github.com/buckyos/cyfs-gateway/issues/64

## 人员汇总
版本 | 版本总分 | 人名 | 个人总分 | 个人总分/版本总分
Beta1 | 1260 | wugren | 707.5 | 56.15%
Beta1 | 1260 | lurenpluto | 432.5 | 34.33%
Beta1 | 1260 | waterflier | 120 | 9.52%
Beta2 | 30 | lurenpluto | 15 | 50.00%
Beta2 | 30 | wugren | 15 | 50.00%

## Item明细
版本 | 人名 | item | item分数 | 属于这个人的分数 | 分摊人数 | 所有负责人 | Status | Module | Priority | URL
Beta1 | lurenpluto | Base Command Implementation | 120 | 120 | 1 | lurenpluto | Done |  | P0 | https://github.com/buckyos/cyfs-gateway/issues/38
Beta1 | lurenpluto | Collection Command Implementation | 60 | 60 | 1 | lurenpluto | Done |  | P1 | https://github.com/buckyos/cyfs-gateway/issues/40
Beta1 | lurenpluto | Process_Chains Framework Implementation | 90 | 90 | 1 | lurenpluto | Done |  | P0 | https://github.com/buckyos/cyfs-gateway/issues/41
Beta1 | lurenpluto | Protocol Detection Command Implementation | 30 | 30 | 1 | lurenpluto | Done |  | P1 | https://github.com/buckyos/cyfs-gateway/issues/39
Beta1 | lurenpluto | SOCKS5 Server | 25 | 12.5 | 2 | lurenpluto, wugren | Done | cyfs-socks | P1 | https://github.com/buckyos/cyfs-gateway/issues/36
Beta1 | lurenpluto | Support JS Engine | 90 | 90 | 1 | lurenpluto | Done |  | P1 | https://github.com/buckyos/cyfs-gateway/issues/45
Beta1 | lurenpluto | Support Lib Calling | 30 | 30 | 1 | lurenpluto | Done |  | P1 | https://github.com/buckyos/cyfs-gateway/issues/43
Beta1 | waterflier | Constructing a multi-node virtual machine development and testing environment based on multipass | 30 | 30 | 1 | waterflier | Done |  | P1 | https://github.com/buckyos/cyfs-gateway/issues/55
Beta1 | waterflier | HTTP Server | 40 | 20 | 2 | waterflier, wugren | Done | http-server | P0 | https://github.com/buckyos/cyfs-gateway/issues/37
Beta1 | waterflier | Impl QA-Server | 30 | 30 | 1 | waterflier | Done |  | P1 | https://github.com/buckyos/cyfs-gateway/issues/51
Beta1 | waterflier | Implementing Web3 gateway with user-held TLS certificates based on TLS stack. | 30 | 30 | 1 | waterflier | Done |  | P0 | https://github.com/buckyos/cyfs-gateway/issues/53
Beta1 | waterflier | Process chain日志级别调整 | 10 | 10 | 1 | waterflier |  |  | P1 | https://github.com/buckyos/cyfs-gateway/issues/62
Beta1 | wugren | ACMA Automatic Certificate Management | 30 | 30 | 1 | wugren | Done | tls-stack | P1 | https://github.com/buckyos/cyfs-gateway/issues/46
Beta1 | wugren | ACME Automatic Certificate Management Support DNS Challenge and HTTP Challenge | 30 | 30 | 1 | wugren | Done | tls-stack | P1 | https://github.com/buckyos/cyfs-gateway/issues/48
Beta1 | wugren | Active Connection Management | 15 | 15 | 1 | wugren | Done |  | P1 | https://github.com/buckyos/cyfs-gateway/issues/30
Beta1 | wugren | Beta1 doc | 30 | 30 | 1 | wugren | Done | document | P0 | https://github.com/buckyos/cyfs-gateway/issues/47
Beta1 | wugren | Command Line Implementation | 30 | 30 | 1 | wugren | Done | cyfs-gateway-cli | P1 | https://github.com/buckyos/cyfs-gateway/issues/33
Beta1 | wugren | CYFS-Gateway Execution Framework | 30 | 30 | 1 | wugren | Done |  | P1 | https://github.com/buckyos/cyfs-gateway/issues/28
Beta1 | wugren | DNS Inner Service Refactoring | 15 | 15 | 1 | wugren | Done | cyfs-dns | P1 | https://github.com/buckyos/cyfs-gateway/issues/34
Beta1 | wugren | HTTP Server | 40 | 20 | 2 | waterflier, wugren | Done | http-server | P0 | https://github.com/buckyos/cyfs-gateway/issues/37
Beta1 | wugren | Packet Interception | 30 | 30 | 1 | wugren | Done | ip-stack | P1 | https://github.com/buckyos/cyfs-gateway/issues/24
Beta1 | wugren | Product Logging Library | 15 | 15 | 1 | wugren | Done |  | P1 | https://github.com/buckyos/cyfs-gateway/issues/29
Beta1 | wugren | QUIC Stack | 30 | 30 | 1 | wugren | Done | quic-stack | P1 | https://github.com/buckyos/cyfs-gateway/issues/22
Beta1 | wugren | QUIC Tunnel Support | 10 | 10 | 1 | wugren | Done | quic-stack | P1 | https://github.com/buckyos/cyfs-gateway/issues/31
Beta1 | wugren | Rate Limiting Implementation | 30 | 30 | 1 | wugren | Done |  | P1 | https://github.com/buckyos/cyfs-gateway/issues/25
Beta1 | wugren | RTCP Refactoring | 10 | 10 | 1 | wugren | Done | rtcp-stack | P1 | https://github.com/buckyos/cyfs-gateway/issues/26
Beta1 | wugren | rtcp stack | 20 | 20 | 1 | wugren | Done | rtcp-stack | P0 | https://github.com/buckyos/cyfs-gateway/issues/21
Beta1 | wugren | SN Inner Service Refactoring | 45 | 45 | 1 | wugren | Done |  | P1 | https://github.com/buckyos/cyfs-gateway/issues/35
Beta1 | wugren | SN refactor | 30 | 30 | 1 | wugren | Done |  | P1 | https://github.com/buckyos/cyfs-gateway/issues/68
Beta1 | wugren | SOCKS5 Server | 25 | 12.5 | 2 | lurenpluto, wugren | Done | cyfs-socks | P1 | https://github.com/buckyos/cyfs-gateway/issues/36
Beta1 | wugren | Support for configuring global collections | 20 | 20 | 1 | wugren | Done |  | P1 | https://github.com/buckyos/cyfs-gateway/issues/65
Beta1 | wugren | Support traffic statistics and speed limiting by user | 60 | 60 | 1 | wugren | Done |  | P1 | https://github.com/buckyos/cyfs-gateway/issues/50
Beta1 | wugren | Supports HTTPS request certificate replacement | 30 | 30 | 1 | wugren | Done | http-server | P1 | https://github.com/buckyos/cyfs-gateway/issues/49
Beta1 | wugren | System Integration | 30 | 30 | 1 | wugren | Done | cyfs-gateway-cli | P1 | https://github.com/buckyos/cyfs-gateway/issues/44
Beta1 | wugren | tcp stack | 20 | 20 | 1 | wugren | Done | ip-stack | P0 | https://github.com/buckyos/cyfs-gateway/issues/19
Beta1 | wugren | TLS Stack | 20 | 20 | 1 | wugren | Done | rtcp-stack | P0 | https://github.com/buckyos/cyfs-gateway/issues/23
Beta1 | wugren | Tun Device Packet Interception | 45 | 45 | 1 | wugren | Done |  | P1 | https://github.com/buckyos/cyfs-gateway/issues/32
Beta1 | wugren | TunnelManager Refactoring | 10 | 10 | 1 | wugren | Done |  | P1 | https://github.com/buckyos/cyfs-gateway/issues/27
Beta1 | wugren | udp stack | 20 | 20 | 1 | wugren | Done | ip-stack | P0 | https://github.com/buckyos/cyfs-gateway/issues/20
Beta1 | wugren | web3 gateway test | 20 | 20 | 1 | wugren | Done | test | P1 | https://github.com/buckyos/cyfs-gateway/issues/56
Beta2 | lurenpluto | cyfs-gateway provides better debugging tools for process chains. | 30 | 15 | 2 | lurenpluto, wugren | Done |  | P1 | https://github.com/buckyos/cyfs-gateway/issues/64
Beta2 | wugren | cyfs-gateway provides better debugging tools for process chains. | 30 | 15 | 2 | lurenpluto, wugren | Done |  | P1 | https://github.com/buckyos/cyfs-gateway/issues/64

## 原始数据
Title | URL | Assignees | Status | Module | Priority | Score | Result | Milestone | Start | Target date
Beta1 doc | https://github.com/buckyos/cyfs-gateway/issues/47 | wugren | Done | document | P0 | 30 | 30 | Beta1
Command Line Implementation | https://github.com/buckyos/cyfs-gateway/issues/33 | wugren | Done | cyfs-gateway-cli | P1 | 30 | 30 | Beta1 | Sep 22, 2025 | Sep 26, 2025
System Integration | https://github.com/buckyos/cyfs-gateway/issues/44 | wugren | Done | cyfs-gateway-cli | P1 | 30 | 30 | Beta1 | Oct 13, 2025 | Nov 21, 2025
Constructing a multi-node virtual machine development and testing environment based on multipass | https://github.com/buckyos/cyfs-gateway/issues/55 | waterflier | Done |  | P1 | 30 | 30 | Beta1
cyfs-gateway provides better debugging tools for process chains. | https://github.com/buckyos/cyfs-gateway/issues/64 | lurenpluto, wugren | Done |  | P1 | 30 | 30 | Beta2
Implementing Web3 gateway with user-held TLS certificates based on TLS stack. | https://github.com/buckyos/cyfs-gateway/issues/53 | waterflier | Done |  | P0 | 30 | 30 | Beta1
SN Inner Service Refactoring | https://github.com/buckyos/cyfs-gateway/issues/35 | wugren | Done |  | P1 | 45 | 45 | Beta1
web3 gateway test | https://github.com/buckyos/cyfs-gateway/issues/56 | wugren | Done | test | P1 | 20 | 20 | Beta1
SN refactor | https://github.com/buckyos/cyfs-gateway/issues/68 | wugren | Done |  | P1 | 30 | 30 | Beta1
HTTP Server | https://github.com/buckyos/cyfs-gateway/issues/37 | waterflier, wugren | Done | http-server | P0 | 30 | 40 | Beta1
DNS Inner Service Refactoring | https://github.com/buckyos/cyfs-gateway/issues/34 | wugren | Done | cyfs-dns | P1 | 15 | 15 | Beta1
SOCKS5 Server | https://github.com/buckyos/cyfs-gateway/issues/36 | lurenpluto, wugren | Done | cyfs-socks | P1 | 30 | 25 | Beta1
Supports HTTPS request certificate replacement | https://github.com/buckyos/cyfs-gateway/issues/49 | wugren | Done | http-server | P1 | 30 | 30 | Beta1
Impl QA-Server | https://github.com/buckyos/cyfs-gateway/issues/51 | waterflier | Done |  | P1 | 30 | 30 | Beta1
tcp stack | https://github.com/buckyos/cyfs-gateway/issues/19 | wugren | Done | ip-stack | P0 | 15 | 20 | Beta1
udp stack | https://github.com/buckyos/cyfs-gateway/issues/20 | wugren | Done | ip-stack | P0 | 15 | 20 | Beta1
TLS Stack | https://github.com/buckyos/cyfs-gateway/issues/23 | wugren | Done | rtcp-stack | P0 | 15 | 20 | Beta1
rtcp stack | https://github.com/buckyos/cyfs-gateway/issues/21 | wugren | Done | rtcp-stack | P0 | 15 | 20 | Beta1 | Sep 15, 2025 | Sep 19, 2025
QUIC Stack | https://github.com/buckyos/cyfs-gateway/issues/22 | wugren | Done | quic-stack | P1 | 30 | 30 | Beta1
RTCP Refactoring | https://github.com/buckyos/cyfs-gateway/issues/26 | wugren | Done | rtcp-stack | P1 | 10 | 10 | Beta1 | Sep 15, 2025 | Sep 19, 2025
Packet Interception | https://github.com/buckyos/cyfs-gateway/issues/24 | wugren | Done | ip-stack | P1 | 30 | 30 | Beta1 | Sep 22, 2025 | Sep 26, 2025
QUIC Tunnel Support | https://github.com/buckyos/cyfs-gateway/issues/31 | wugren | Done | quic-stack | P1 | 5 | 10 | Beta1 | Sep 15, 2025 | Sep 19, 2025
Tun Device Packet Interception | https://github.com/buckyos/cyfs-gateway/issues/32 | wugren | Done |  | P1 | 45 | 45 | Beta1
ACMA Automatic Certificate Management | https://github.com/buckyos/cyfs-gateway/issues/46 | wugren | Done | tls-stack | P1 | 30 | 30 | Beta1
ACME Automatic Certificate Management Support DNS Challenge and HTTP Challenge | https://github.com/buckyos/cyfs-gateway/issues/48 | wugren | Done | tls-stack | P1 | 30 | 30 | Beta1
Base Command Implementation | https://github.com/buckyos/cyfs-gateway/issues/38 | lurenpluto | Done |  | P0 | 60 | 120 | Beta1
Process_Chains Framework Implementation | https://github.com/buckyos/cyfs-gateway/issues/41 | lurenpluto | Done |  | P0 | 90 | 90 | Beta1
CYFS-Gateway Execution Framework | https://github.com/buckyos/cyfs-gateway/issues/28 | wugren | Done |  | P1 | 30 | 30 | Beta1 | Sep 9, 2025 | Sep 19, 2025
TunnelManager Refactoring | https://github.com/buckyos/cyfs-gateway/issues/27 | wugren | Done |  | P1 | 10 | 10 | Beta1 | Sep 15, 2025 | Sep 19, 2025
Rate Limiting Implementation | https://github.com/buckyos/cyfs-gateway/issues/25 | wugren | Done |  | P1 | 30 | 30 | Beta1 | Sep 3, 2025 | Sep 12, 2025
Product Logging Library | https://github.com/buckyos/cyfs-gateway/issues/29 | wugren | Done |  | P1 | 30 | 15 | Beta1
Active Connection Management | https://github.com/buckyos/cyfs-gateway/issues/30 | wugren | Done |  | P1 | 15 | 15 | Beta1 | Sep 3, 2025 | Sep 12, 2025
Protocol Detection Command Implementation | https://github.com/buckyos/cyfs-gateway/issues/39 | lurenpluto | Done |  | P1 | 30 | 30 | Beta1
Collection Command Implementation | https://github.com/buckyos/cyfs-gateway/issues/40 | lurenpluto | Done |  | P1 | 60 | 60 | Beta1
Support Lib Calling | https://github.com/buckyos/cyfs-gateway/issues/43 | lurenpluto | Done |  | P1 | 30 | 30 | Beta1
Support JS Engine | https://github.com/buckyos/cyfs-gateway/issues/45 | lurenpluto | Done |  | P1 | 90 | 90 | Beta1
Support traffic statistics and speed limiting by user | https://github.com/buckyos/cyfs-gateway/issues/50 | wugren | Done |  | P1 | 60 | 60 | Beta1
Support for configuring global collections | https://github.com/buckyos/cyfs-gateway/issues/65 | wugren | Done |  | P1 | 20 | 20 | Beta1
Process chain日志级别调整 | https://github.com/buckyos/cyfs-gateway/issues/62 | waterflier |  |  | P1 | 10 | 10 | Beta1
Add map command design and support to process chain | https://github.com/buckyos/cyfs-gateway/issues/11 | lurenpluto | Done |  |  |  |  | Beta1
Full HTTPS Support for cyfs-wrap | https://github.com/buckyos/cyfs-gateway/issues/12 | lurenpluto, photosssa, waterflier | Ready |  |  |  |  | Beta1
fix ipv6 support bug | https://github.com/buckyos/cyfs-gateway/issues/94 | waterflier | [5 empty] | Beta1